## Slide 1: ISER Steering Committee Proposal Presented to the Planning & Budgeting Council (serving at the College’s Accreditation Oversight Committee) on November 1, 2023 by Karen Engel, Dean of PRIE and Accreditation Liaison Officer

## Slide 2: Overseeing the College’s Institutional Self Evaluation Report (ISER) Preparation
The PBC serves as the College’s Accreditation Oversight Committee
Starting in Spring 2024, more oversight and guidance will be needed to prepare our ISER
Proposal: establish an Accreditation Steering Committee

## Slide 3: Duties of the Steering Committee
Look at the required evidence for each Standard
Help identify individuals and groups on campus best positioned to help find evidence for each Standard
Advise the Accreditation Liaison Officer and Faculty Accreditation Lead in determining how to best address gaps in evidence that are found
Review drafts of the Institutional Self Evaluation Report and facilitate campus participation as needed

## Slide 4: Composition of the Steering Committee
Tri-Chairs for Standard 1
Tri-Chairs for Standard 2
Tri-Chairs for Standard 3
Tri-Chairs for Standard 4
Accreditation Liaison Officer
Accreditation Faculty Lead
Administrators as needed
College President
Tri-Chairs: one each from:
Faculty
Classified Staff
Administration

## Slide 5
Proposed Initial Approach for Identifying Administrative, Senate, Council, and Committee Leads for Each Standard

## Slide 6
Proposed Initial Approach for Identifying Administrative, Senate, Council, and Committee Leads for Each Standard

## Slide 7
Proposed Initial Approach for Identifying Administrative, Senate, Council, and Committee Leads for Each Standard

## Slide 8
Proposed Initial Approach for Identifying Administrative, Senate, Council, and Committee Leads for Each Standard

## Slide 9
 | Initial Timeline for ISER Preparation: 2023-2025
Fall 2023 | PBC (Accreditation Oversight Committee) reviews new Standards and adopts overall timeline for the Self Evaluation process Administrative Leads for each Standard review new Standards and expectations for the Self-Evaluation Process with College Councils and Senates PBC forms an ISER Steering Committee that includes faculty, classified staff, and student leaders to join Administrative leads for each Section of the ISER to begin work in Spring/Fall 2024
Spring 2024 | Accreditation Steering Committee develops detailed plan for Report preparation. Administrative and Senate Leads begin identifying and collecting evidence. Administrative and Senate Leads identify any areas that need to be addressed (where evidence may be lacking) and presents these to PBC. PBC recommends how to address gaps in practice or evidence and Administrative and Senate leads work with Councils, Senates, and Committees to address them
Fall 2024 | Administrative, Senate, Council and Committee Leads address gaps in evidence, begin collecting and organizing evidence, and drafting brief narratives.
Spring 2025 | First Draft of ISER completed and all evidence gathered and organized.
Fall 2025 | Second and final Draft of ISER completed and submitted to BOT for approval. Final ISER Submitted to ACCJC by December, 2025.

## Slide 10: Information and Resources
Cañada Accreditation Website
ACCJC Resources Website
Accreditation Manual (new as of 2023)